## Week 1
Software Engineering, Final Project: Direction Giving Service With QR Code
Task List
Task |  | Start Date | Who | Days To Complete | Duration (hours) | End Date
Week 1 5th April | Form Team | 2016-04-05 | SC, AA, YK | 2 | 1.5 | 2016-04-12
| Sprint Backlog/Requirements | 2016-04-05 | SC | 4 | 1.5 | 2016-04-12
| Task List | 2016-04-05 | YK | 4 | 1.5 | 2016-04-12
| 1st Draft: UML Diagram/Model | 2016-04-05 | AA | 5 | 1.5 | 2016-04-12
| Get Example Code Working | 2016-04-05 | SC, AA, YK | 5 | 1.5 | 2016-04-12
| Update Gantt Chart | 2016-04-05 | YK | 1 | 0.4 | 2016-04-12
| Total Time Week 1 |  |  | 21 | 7.9
Week 2 12th April | Finialise UML Model | 2016-04-12 | AA | 4 | 1 | 2016-04-19
| Start Code Prototype | 2016-04-12 | SC | 4 | 0.4 | 2016-04-19
| Start Devising Unit Tests | 2016-04-12 | SC | 4 | 1 | 2016-04-19
| Working Examples Of QR Code | 2016-04-12 | SC | 4 | 1 | 2016-04-19
| Update Gnatt Chart | 2016-04-12 | YK | 1 | 0.4 | 2016-04-19
| Total Time Week 2 |  |  | 17 | 3.8
Week 3 19th April | Code Prototype Work | 2016-04-19 | SC, YK | 5 | 1.5 | 2016-04-26
| Run Unit Tests | 2016-04-19 | SC, YK | 4 | 0.4 | 2016-04-26
| Generate Working Examples Of QR Codes | 2016-04-19 | SC, YK | 4 | 1 | 2016-04-26
| Update Gnatt Chart | 2016-04-19 | YK | 1 | 0.4 | 2016-04-26
| Total Time Week 3 |  |  | 14 | 3.3
Week 4 26th April | Run Unit Tests | 2016-04-26 | SC, YK, AA | 3 | 0.5 | 2016-05-03
| Add Features | 2016-04-26 | SC, YK, AA | 3 | 0.5 | 2016-05-03
| Perform Demo Dry Run | 2016-04-26 | SC, YK ,AA | 3 | 0.5 | 2016-05-03
| Update Gnatt Chart | 2016-04-26 | YK | 1 | 0.4 | 2016-05-03
| Total Time Week 4 |  |  | 10 | 1.9
Week 5 3rd May | Ensure Deliverables Are Submitted | 2016-05-03 | YK | 2 | 0.4 | 2016-05-10
| Commit Project to GitHub | 2016-05-03 | SC | 2 | 0.5 | 2016-05-10
| Demo Project In Lab | 2016-05-03 | SC, YK, AA | 1 | 0.5 | 2016-05-10
| Total Time Week 5 |  |  | 5 | 1.4
Total Project Time |  |  |  | 55 | 16

## Week 2
Software Engineering, 4 Week Final Project Timeline
| Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Finish
| April | [6 empty] | April | [6 empty] | April | [6 empty] | April |  |  |  |  | May |  | May
| tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue
| 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Assigned To: | May tue: 12am
Alexandre, Juri, Shaun | April tue: Form Team
Get Example Code Working
Alexandre | April tue: 1st Draft UML Diagram/Model
Juri | April tue: Task List
Update Gnatt Chart
Shaun | April tue: Sprint Backlog/Requirements
Alexandre | April tue: Finalise UML Model
Juri | April tue: Update Gantt Chart
Shaun | April tue: Start Code Prototype
Start devising unit Tests
Working Examples of QR Code
Juti | April tue: Update Gnatt Chart
Juri, Shaun | April tue: Code Prototype Work
Run Unit Tests
Generate Working Examples Of QR Code
Alexandre, Juri, Shaun | April tue: Run Unit Tests
Add Features
Perform Demo Dry Run
Juri | April tue: Update Gnatt Chart
Alexandre, Juri, Shaun | May tue: Demo Project In Lab
Juri | May tue: Ensure Deliverables Are Submitted
Shaun | May tue: Commit Project To GitHub

## Week 3
Software Engineering, 4 Week Final Project Timeline
| Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Finish
| April | [6 empty] | April | [6 empty] | April | [6 empty] | April |  |  |  |  | May |  | May
| tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue
| 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Assigned To: | May tue: 12am
Alexandre, Juri, Shaun | April tue: Form Team
Get Example Code Working
Alexandre | April tue: 1st Draft UML Diagram/Model
Juri | April tue: Task List
Update Gnatt Chart
Shaun | April tue: Sprint Backlog/Requirements
Alexandre | April tue: Finalise UML Model
Juri | April tue: Update Gantt Chart
Shaun | April tue: Start Code Prototype
Start devising unit Tests
Working Examples of QR Code
Juti | April tue: Update Gnatt Chart
Juri, Shaun | April tue: Code Prototype Work
Run Unit Tests
Generate Working Examples Of QR Code
Alexandre, Juri, Shaun | April tue: Run Unit Tests
Add Features
Perform Demo Dry Run
Juri | April tue: Update Gnatt Chart
Alexandre, Juri, Shaun | May tue: Demo Project In Lab
Juri | May tue: Ensure Deliverables Are Submitted
Shaun | May tue: Commit Project To GitHub

## Week 4
Software Engineering, 4 Week Final Project Timeline
| Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Finish
| April | [6 empty] | April | [6 empty] | April | [6 empty] | April |  |  |  |  | May |  | May
| tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue
| 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Assigned To: | May tue: 12am
Alexandre, Juri, Shaun | April tue: Form Team
Get Example Code Working
Alexandre | April tue: 1st Draft UML Diagram/Model
Juri | April tue: Task List
Update Gnatt Chart
Shaun | April tue: Sprint Backlog/Requirements
Alexandre | April tue: Finalise UML Model
Juri | April tue: Update Gantt Chart
Shaun | April tue: Start Code Prototype
Start devising unit Tests
Working Examples of QR Code
Juti | April tue: Update Gnatt Chart
Juri, Shaun | April tue: Code Prototype Work
Run Unit Tests
Generate Working Examples Of QR Code
Alexandre, Juri, Shaun | April tue: Run Unit Tests
Add Features
Perform Demo Dry Run
Juri | April tue: Update Gnatt Chart
Alexandre, Juri, Shaun | May tue: Demo Project In Lab
Juri | May tue: Ensure Deliverables Are Submitted
Shaun | May tue: Commit Project To GitHub

## Week 5
Software Engineering, 4 Week Final Project Timeline
| Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Finish
| April | [6 empty] | April | [6 empty] | April | [6 empty] | April |  |  |  |  | May |  | May
| tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue
| 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Assigned To: | May tue: 12am
Alexandre, Juri, Shaun | April tue: Form Team
Get Example Code Working
Alexandre | April tue: 1st Draft UML Diagram/Model
Juri | April tue: Task List
Update Gnatt Chart
Shaun | April tue: Sprint Backlog/Requirements
Alexandre | April tue: Finalise UML Model
Juri | April tue: Update Gantt Chart
Shaun | April tue: Start Code Prototype
Start devising unit Tests
Working Examples of QR Code
Juti | April tue: Update Gnatt Chart
Juri, Shaun | April tue: Code Prototype Work
Run Unit Tests
Generate Working Examples Of QR Code
Alexandre, Juri, Shaun | April tue: Run Unit Tests
Add Features
Perform Demo Dry Run
Juri | April tue: Update Gnatt Chart
Alexandre, Juri, Shaun | May tue: Demo Project In Lab
Juri | May tue: Ensure Deliverables Are Submitted
Shaun | May tue: Commit Project To GitHub